## Project Plan and Gantt
Project Name | QuanLyNhaSach
Project Manager | Nguyen Hoang Nguyen
Project Deliverable
Scope Statement:
Start Date | 2016-08-19
End Date | 2015-10-10
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Nguyên | 2016-08-19 | 2016-08-21 | 2 | Complete
Agree on objectives | Nguyên | 2016-08-21 | 2016-08-23 | 2 | Complete
Detailed Reqs. | Team | 2016-08-23 | 2016-08-27 | 4 | In progress
Techincal Reqs. | Team | 2016-08-27 | 2016-08-31 | 4 | Not started
DB Development | Nguyên | 2016-08-31 | 2016-09-05 | 5 | Not started
Connect DB | Long | 2016-09-05 | 2016-09-09 | 4 | Not started
Insert/Update/Query | Phát | 2016-09-09 | 2016-09-13 | 4 | Not started
API Development | Nguyên | 2016-09-13 | 2016-09-18 | 5 | Not started
Function 1 | Long | 2016-09-18 | 2016-09-22 | 4 | Not started
Function 2,… | Phát | 2016-09-18 | 2016-09-22 | 4 | Not started
UI Client | Nguyên | 2016-09-22 | 2016-09-27 | 5 | Not started
Testing | Team | 2016-09-27 | 2016-09-30 | 3 | Not started
Dev. Complete | Team | 2016-09-30 | 2016-10-03 | 3 | Not started
Hardware Config. | Team | 2016-10-03 | 2016-10-06 | 3 | Not started
System Testing | Team | 2016-10-06 | 2016-10-09 | 3 | Not started
Launch |  | 2016-10-10 | 2016-10-10 | 0

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Nguyễn Hoàng Nguyên | Team leader | 1. Make the plan of the project. 2. Assign task for your member. 3. Analysis & design the system. 4. Code. 5. Write document | danenguyenvn@gmail.com
Nguyễn Trường Phát | Developer | 1. Design GUI/database. 2. Code. 3. Test | caolua00@gmail.com
Phan Mỹ Long | Developer | 1. Design GUI/database. 2. Code. 3. Test | phanmylong456@gmail.com

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team